## Checklist
Event Management Checklist (Developed by Organisation Development & Design, Kells)
2024-09-13
Section Headings | Action | Responsible | Yes/No/ N/A | Follow Up Actions
1.0 Oversight Responsibilities
1.1 Assign Lead responsibilites in line with Key functions
1.1.1 Agree specific roles on the day: (1) Welcome- Lead Facilitator plus Organisational Change Unit Team or others; (2) Registration – Business Support Team; (3) Meeting guests - Lead Facilitator plus Organisational Change Unit Team or others; (4) Working with Comms team --Comms & Digital Officer plus Business Support Team etc.
1.2 Identify Steering Group and Lead Facilitator
1.2.1 Confirm Steering Group for event, role and communication channels
1.2.2 Confirm Lead facilitator
2.0 Budget
2.1 Outline breakdown of all potential costs re event including comms and marketing expenses (venue, catering, photographer, videographer, AV contractor, guest speakers, event materials, surveys, digital tools etc.)
2.2 Feedback on budget plan to Steering Group or Lead Facilitator for the event and confirm approval process – may vary depending on event
2.3 Troubleshoot logistics if budget transfers are required i.e. between cost centres. Agree what costs are assigned to each cost centre
2.4 Confirm the vendor set up processes re above and associated timescales
2.5 Provide clarity for team members re travel arrangements, accommodation etc if overnight stays are required in alignment in NFR B4 Travel & Subsistence
2.6 Communicate venue or changes in budget to Steering Group or Lead Facilitator
3.0 Pre Event Logistics/Planning - Venue
3.1 Agree suitable date
3.2 Identify venue for event
3.3 Identify person who will act as primary contact with the venue
3.4 Identify Event Manager and clarify contact details to troubleshoot
3.5 Agree communication schedule and method of communication (email or other) with Event Manager
3.6 Agree costing with the venue – address how last minute changes will be accommodated i.e. numbers attending on the day are more or less than confirmed in advance etc. Clarify cancellation policy
3.7 Agree schedule for refreshments/food including giving notice for breaks, noting arrangement for special dietary requirements etc.
3.8 Agree requirement for tables i.e. water, fruit and replenishments during the day
3.9 Confirm venue meets all accessibility requirements for potential attendees, car parking, wheelchair accessibility etc.
3.10 Confirm the room meets all tech requirements for the event
3.11 Agree room layout and any special room requirements
3.12 Clarify expectations on the day with Event Manager
3.13 Confirm booking in writing and outline all agreed requirements-using above points as baseline for communication
3.14 Closer to the date confirm projected number of attendees
4.0 Exhibition/Poster Stands Management
4.1 Provide guidance for stands at the event if relevant - see link below for suggestions
Comms for Marketplace Exhibitors PPC 2024.docx
4.2 Provide guidance re developing poster presentations see helpful advice:
Email Helpful advice re; Poster Presentation Guidance 16.08.24.msg
5.0 Attendee Management
5.1 Agree approach to inviting staff – who issues the invite (CEO, REO, other)?
5.2 Identify who is being invited to event and confirm invitation list
5.3 Consider accessibility issues re disability, language, use of interpreters, sign language etc.
5.4 Create attendee list in a format that is user friendly and adaptable to needs (Format Excel file, consider event management system i.e. Event Brite or other system used in the HSE – webinar series)
5.5 Consider how excel file will transfer to creation of name badges, seated table plan etc.
5.6 Agree process to track acceptance/non acceptance invitations via excel file or agreed process
5.7 Prepare invitation content
5.8 Agree when invite needs to be issued
5.9 Agree if reminder needs to be issued – update details
5.10 Agree what data needs to go to attendees in advance i.e. GPPR consent form
5.11 Agree how consent will be managed (1) sign on the day to provide consent or (2) circulate consent form with invitation
5.12 Provide details to attendees re how to access the venue
5.13 Agree catering arrangements with attendees and speakers noting any special dietary needs – feedback to venue
5.14 Disseminate timetable /agenda for the day with attendees – be clear on start and finish times
5.15 Access data re taxis or other details that will assist potential attendees
5.16 Clarify if it is a hybrid event – combination of in-person and virtual - share link in advance and test on the day
5.17 Consider if an event landing page is required – share with attendees
5.18 Ensure all comms teams are kept in the loop
5.19 Consider how last minute changes can be accommodated
5.20 Agree policy on late applicants
5.21 Note any special guests or related protocols that may be required i.e. CEO, Minister etc.
5.22 Ensure consent for photography / videography is agreed - work out contingency plan if some individuals do not consent
5.23 Agree table plan pre event
5.24 Agree seating plan if individuals are assigned to specific tables
5.25 Clarify any pre work needed in advance of the event
5.26 Follow up with attendees who could not attend on the day – share materials as relevant
6.0 Conference/Workshop Details
6.1 Create list of items needed to run the event with the lead facilitators
6.2 Agree schedule for the day with lead facilitator – this will impact on room layout
6.3 Work out the room layout (tables, chairs, podium, stage, top table, location of AV equipment and associate personnel, location of flip chart stands, backdrop on the stage etc.)
6.4 Determine if any changes are needed throughout the day (make sure to keep venue leads informed)
6.5 Review seating and furniture plan with venue to ensure it meets event requirements
6.6 Determine ventilation and air conditioning
6.7 Identify requirement to run event – name badges, flip board pads, static white board sheets, markers, pens, sticky notes, other items for the tables, blue tac etc.
6.8 Identify additional comms materials if needed – roller banners, posters
6.9 Agree if signage is needed to help people locate room in the venue
6.10 Order items as noted above re stationary and comms – allow time for delivery
6.11 Agree if breakout rooms are needed and agree with venue
6.12 Organise side room if needed to record interviews
6.13 Agree get in and get out time re venue
6.14 Agree time to access the venue to set up the room (night before or early morning)
6.15 Agree who will complete room set up and ensure they are fully informed and have all the materials they need to hand
6.16 Ensure seating plan in room is clear – numbers on tables or colour coding
6.17 Complete sound check, tech check, carry out pre event run through, rehearsal re sequencing
6.18 If it is a hybrid event – combination of in-person and virtual – follow up re arrangements re virtual including ICT needs and sharing links in advance – always do a trial run
6.19 Clarify if large screens are needed for slide presentations – work out location in the venue for visibility and room layout
6.20 Confirm Wi-Fi and password – share as appropriate with participants
6.21 Think contingency – what might go wrong and what back up plan do you need to run the event?
7.0 Administration to assist in Event
7.1 Consider if an event landing page is required and assign responsibility to set it up and keep it updated
7.2 Include schedule or running order for the day, hashtags, bios for any speakers and some helpful info like transport links, numbers for taxis etc.
7.3 Set up access to Share file account to facilitate in sharing files, photos etc.
8.0 Guest Speakers
8.1 Provide guidance to speakers in advance including agreed slide templates (note these will need to be adapted to the event). If event is aligned to Organisational Change Unit appropriate slide templates need to be provided
Guidelines for Speakers 21Aug24.docx
Helpful Conference Presentation Template Aug 24.pptx
8.1.1 Make arrangements for guest speakers / presenters / panellists
8.1.2 Agree if MC is needed and make contact – agree role and brief in advance
8.1.3 Agree fee and associated method for payment
8.1.4 Confirm travel arrangements – flights, taxis
8.1.5 Confirm accommodation
8.1.6 Identify ICT needs and associated compatibility
8.1.7 Source presentations and materials they may be sharing including video links
8.1.8 Consider person to be the primary link with guest speakers on the day
8.1.9 Confirm dietary needs, preferences re photography etc.
8.1.10 Agree if pre meeting needs to be set up to brief speakers, panellist – set up if needed
8.1.10 Share briefing materials to ensure up to speed
8.1.11 Follow up posts event and acknowledge – share key outputs
9.0 Conference / workshop details – content prep
9.1 Agree with lead facilitator what prep work is needed in advance re content for event
9.2 Agree timings for event linked to agenda
9.3 Determine if workshops are planned and need for breakout rooms
9.4 Sign off on event agenda – build in time for modifications as needs change
9.5 Ensure slide decks are prepared on agreed templates; proof for accuracy and quality check re layout and consistency
9.6 Build in time for last minute changes
9.7 Agree process for liaising with external presenters on accessing their presentations
9.8 Agreed who will collate complete slide decks and quality assure
9.9 Agree process to share complete slide decks with AV company in advance – provide schedule to assist on the day – sequence and associated timelines
9.10 Have a contingency back up plan – always have slides on USB or other source as needed in case of technical issues
9.11 Agree with Lead Facilitator how data is being shared and clarify how
9.12 Design post event feedback survey
10.0 Ceremonial Aspects
10.1 Prepare /source materials for awards certificates if relevant
10.2 Agree design and layout in advance
10.3 Agree process to quality assure re accuracy of correct names/service details
10.4 Walk through how certificates will be presented on the day (‘dry run’) to ensure professional and smooth approach – who will present the certs, in what sequence, where will this take place, where people need to wait or stand
10.5 Follow up with people unable to attend on the day
10.6 Consider music or other elements to add to the atmosphere
11.0 Resource Distribution
11.1 Agree resource distribution plan pre, during and post event
11.2 Ensure adequate resource supplies are available, order well in advance and agree courier if needed
11.3 Prepare attendee packs in advance and ensure available at registration desk or as agreed
11.4 Consider how resources will be displayed, shared at the event – seat drop, display table, conference pack, positioning of roller banners etc.
11.4.1 Check that the correct roller banner is being used to reflect the event, labelled as roller banners may look similar and all is in working order
11.5 Consider location of marketing or resource materials in area of highest footfall for maximum impact
11.6 Ensure unused resource are collected and returned to source
12.0 Registration
12.1 Ensure all signage to conference room /registration desk is in place
12.2 Prepare attendees sign in template in advance – assess for ease of use and speed
12.3 Set up registration tables and use A-Z to avoid clogging up the space
12.4 Assemble and display name identification badges for collection at registration
12.5 Collect GDPR forms or request people to sign re content
12.6 Inform comms team discreetly if people who “do not consent”
12.7 Agree process to assign people to tables if needed – colour coding or table numbering
12.8 Follow up if attendee list needs to be shared post event
12.9 Alert to any follow up with people who cancelled or could not attend on the day
13.0 Running event on the day
13.1 Agree a running order detailing the schedule for the day. Confirm any changes to the schedule on the day re refreshment breaks
13.2 Ensure sign off with lead facilitator
13.3 Distribute to all involved in the event
13.4 Agree process to notify people of last minute changes
13.5 Include timetable in presentations on the screen at the beginning and in between sessions to keep attendees informed
13.6 Ensure reference to photographs and consent is mentioned at opening of event
13.7 Agree other housekeeping notices at opening of event i.e. fire exits
13.8 Confirm with Event Manager on the day actual number of attendees for food/refreshments purposes
13.9 Ensure tables are marked if attendees are going to be assigned
13.10 Have a visual seating chart in order for attendees to locate their table
13.11 Maintain tight schedule – agree timekeepers and method to signal running over time (cards)
13.12 Agree process to calibrate as needed if running over time
13.13 Set up MENTI and agree timing
13.14 Complete event feedback survey
13.15 Agree plan to clear and tidy room on the day and remove all materials
14.0 AV Support on the Day
14.1 Book freelance AV support and equipment
14.2 Ensure compatibility of tech equipment with the venue in advance
14.3 List and check all AV equipment
14.4 Confirm work plan and requirements from AV company in line with event schedule and sequence of events
14.5 Confirm format required by AV company to receive relevant files – slides, videos, recordings, music, animations, logos
14.6 Ensure full slide deck of PowerPoint slides from all speakers are merged and shared in advance
14.7 Reconfirm sequence of use on the day
14.8 Ensure microphones for presenters, roaming mics are available – test and agree timing for fittings
14.9 On the morning of event: provide guidance for use of microphones with specific focus on panel members
14.10 Carry out tech check on location and trouble shoot issues with venue or AV company
14.11 Confirm Internet/Wi-Fi connectivity in venue
14.12 Provide password for Wi-Fi with delegates /organisers if appropriate
15.0 Survey Methods – on the Day or Post Event
15.1 Agree if survey or other digital tools will be used at event – agree sequence and timing
15.2 Trial run use of Mentimeter or other similar platforms to ensure accessibility and usability on the day. Trouble shoot as needed
15.3 Ensure licence is available to use methods such as Smart Survey, Mentimeter – build into budget plan
16.0 Communications and Marketing Plan
16.1 Agree detail, scale of communications and marketing plan in advance with relevant Steering Group or lead facilitator
16.2 Clarify associated budget
16.3 Agree branding, use of logos, document layout – ensure access to hi res versions as needed, provide templates to assist
16.4 Be mindful of partnerships and ensure appropriate acknowledgement and agreement on logos or other branding matters
16.5 Agree if roller banners are being used – ensure all partners are notified to bring theirs along
16.6 Agree location and set up on the day - location is everything so utilise the room to optimise opportunities provided for recording devices and photography
16.7 Agree social media hashtags for the event to assist in social media coverage
16.8 Include on screen presentations and holding graphics – encourage attendees to join online conversations
17.0 Develop Communications Briefs and Agree Contracts
17.1 Agree process re content of brief: Photographer, Videographer, AV team, Social Media lead
17.2 Agree process of engagement with national or regional communication teams
17.3 Agree how materials will be used at all levels to optimise on materials available – avoid duplication of efforts
17.4 Decide if a QR code is needed for event – agree how this will be developed and accessed on the day. Check that it works on range of devices
17.5 Agree contracting arrangement with providers (photography, videos etc.)
17.6 Follow the Media Relations Protocol for staff submitted 25/09/2024– see guidance at this hyperlink: https://www.hse.ie/eng/services/news/newsresources/commstoolkit/media-relations-protocols.pdf
18.0 Press Release and Key Messaging
18.1 Agreed key messaging for event, confirm with senior leaders and share with comms team
18.2 Agree process to draft, proof, edit and sign off on press release, pre event communications, on the day comms and post event reports
18.3 Agree how comms materials will be shared i.e. email, shared files etc.; by whom and through what methods i.e. HSE staff updates, Website, Change &Innovation Hub, News and Events Page/s, Submission to Newspapers, Radio etc.
18.4 Agree what will be submitted to Health Matters or other publication and build in timescales in advance – consider layout and inclusive of photographs, scanner codes or live website links
19.0 Social Media Management
19.1 Agree approach to social media management including X and LinkedIn – content to be agreed in advance, lead role on the day to craft the content, post event follow up
19.2 Agree templates for above in advance using agreed branding for the event
19.3 Identify who will post social media messages on the day on behalf of the team
20.0 Photography
20.1 Agree plan in advance of photos needed at the event – people, grouping, possible locations, action photos, capturing the atmosphere, people circulating, capturing award ceremony, etc.
20.2 Ensure consent is agreed for photography
20.3 Schedule meeting in advance to discuss expectations of the day
20.4 Agree timescales for follow up – some photos may be needed immediately after the event
20.5 Agree arrangements for group photos -clear communication re; the order of groups to be taken
21.0 Videography
21.1 Agree plan in advance – what needs to be recorded – people arriving, key presentation, Q&A sessions, award ceremony, key moment, group work etc.
21.2 Ensure consent is agreed for videography
21.3 Schedule meeting in advance to discuss expectations of the day
21.4 Agree timescales for follow up – some videos may be needed immediately after the event, others may need to be edited etc
21.5 Agree process to capture sound bites from the beginning/end of the event
22.0 Post Event Comms Follow up
22.1 Work out plan for post event follow up with photographer and videographer
22.2 Select photos and add names and captions
22.3 Review videos and select key moments for edits
22.4 Agree process to share above with participants, senior leaders, comms
22.5 Ensure guidance provided in advance re branding – top and tail of videos
22.6 Agree what needs to be shared on social channels – wording and visuals
22.7 Extract key quotations from videos, transcribe and agree use
22.8 Agree use re testimonials
22.9 Update News and Events on website, on C&I Hub
22.10 Agree process to draft and agree content of post event reports / articles
22.11 Submit articles with photos to Health Matters
22.12 Upload videos to YouTube channel and update catalogue
22.13 Follow up with attendees who could not attend on the day – share comms materials as relevant
23.0 Follow up Post Event
23.1 Draft and send acknowledgements to participants and guest speakers etc.
23.2 Record new contacts and associated follow up
23.3 Follow up re financial management – paying all associated costs including venue re; billing invoices/processing payments
23.4 Complete budget transfer if needed
23.5 Complete budget statement and share with Steering Group /lead facilitator
23.6 Validate guest speaker and staff travel claims, accommodation or other expenses
23.7 Complete Performance Metrics - referral & intervention database with number of participants.
23.8 Complete social media metrics
23.9 Complete an After Action Review of event – share key learnings
23.10 Follow up re Smart Survey results and document findings
23.11 Follow up with CPD process for programme if relevant
23.12 Complete event report
We wish to acknowledge the following reference sources: (1) HSE National Communications (2) Patient & Service User Experience, HSE Public Involvement, Culture and Risk Management (3) HSE Conference Planning Team - Integrated Healthcare: Advancing Health Service Reform (4) HSE CHO1 Comms - Media Relations Protocol for staff
Material from this document should be referenced as: Health Service Executive - HSE Organisational Change Unit - Organisation Development & Design (2024). Event Management Checklist. Kells, Co Meath, Ireland: Health Service Executive.
Disclaimer: In developing the Event Management Checklist we have gathered and adapted information and knowledge from many sources. We always seek to do this in a way that respects the work of other people and acknowledges the source of the content. Based on the data available to us the content was accurate at the time of development. In relation to National HSE guidance please refer to the most up to date documents / guidance on the HSE website or contact National Communications in this regard.
Organisation Development & Design, HSE Organisational Change Unit, Kells, Co Meath. © Health Service Executive 2024
changeguide@hse.ie │ www.hse.ie/changeguide │ https://linktr.ee/hsechangeguide │ change & innovation hub: www.hseland.ie